## Sprint 2 Backlog
[5 empty] | Points Remaining |  | Points Completed
User story | Breakdown | Tasks | Additional breakdown | Points |  | Assignees | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Complete
As a user I would like to have a quiz that can test my general knowledge that works on my laptop, phone or tablet | SPIKE backend | Investigate cloud infrastructure |  | 1 | 0 | Robert |  | 1 |  |  |  | Yes
|  | Investigate Backend Technologies |  |  | 0 | Jason, Robert, Ryan,Matthew | [5 empty] | Yes
|  |  | nodejs + express | 2 | 0 | Robert | 2 |  |  |  |  | Yes
|  |  | flask | 2 | 0 | Jason | 2 |  |  |  |  | Yes
|  |  | .NET | 2 | 0 | Ryan | 2 |  |  |  |  | Yes
|  | Node Test |  | 2 | 2 | Jason | [5 empty] | No
|  | Find dataset |  | 2 | 2 | Jason | [5 empty] | No
|  | Research Sync Communication between clients and server |  | 3 | 3 | Robert, Paul, Ryan | [5 empty] | No
| Database setup | Node Server Setup |  | 3 | 3 | Robert | [5 empty] | No
|  | Define API schema |  | 2 | 2 | Ryan | [5 empty] | No
|  | Populate DB |  | 1 | 1 | Robert | [5 empty] | No
|  | Dataset to JSON |  |  | 0 | [6 empty] | Yes
|  | create cloud Infrastructure for Node and DB |  | 2 | 2 | [6 empty] | No
[5 empty] | 0 | [6 empty] | Yes
|  |  | Cloud intigration Research | 2 | 0 | Mathew | 2 |  |  |  |  | Yes
As a user I can initialise a single player quiz | SPIKE Frontend | Research Angular Framework |  |  | 8 | Lachlan, Matt, Alek | [5 empty] | No
|  |  | Research | 5 | 0 | Lachlan | 1 | 4 |  |  |  | Yes
|  |  | Research | 4 | 4 | Matt | [5 empty] | No
|  |  | Research | 4 | 4 | Alek | [5 empty] | No
|  | Investigate UX for quiz |  | 2 | 0 | Lachlan | 1 | 1 |  |  |  | Yes
|  | Investigate possibility of teams plugins |  | 3 | 3 | Mikhail | [5 empty] | No
| Frontend Wireframe | Design Quiz page |  | 1 | 0 | Matt | 1 |  |  |  |  | Yes
|  | Design opening Page |  | 1 | 0 | Matt | 1 |  |  |  |  | Yes
|  | Design end of Quiz Page |  | 1 | 0 | Matt | 1 |  |  |  |  | Yes
| Create Angular Quiz Prototype | Front Page |  | 4 | 0 | Rauf | 2 | 2 |  |  |  | Yes
|  | Quiz Setting Page |  | 4 | 1 | Lachlan |  |  | 2 | 1 |  | No
|  | Host Setting Page |  | 4 | 4 | Mikhail | [5 empty] | No
|  | Quiz Game Page |  | 8 | 8 | Rauf | [5 empty] | No
|  | Quiz Game Page |  | 4 | 4 | Ruaf | [5 empty] | No
Integration and Documentation | Integration Management | Receiving Data from Database |  |  | 0 | [6 empty] | Yes
Investigate games integration into teams |  |  |  |  | 0 | [6 empty] | Yes
[5 empty] | 0 | [6 empty] | Yes
| Daily Documentation Updates | Update sprint backlog, notes, product backlog |  | 5 | 2 | Lachlan | 1 | 1 | 1 |  |  | No
[5 empty] | 0 | [6 empty] | Yes

## Team Roster
Name | Matriculation Number | Email Address

## Analytics
Total Points for Sprint
74 |  |  |  | 0
Points Remaining
Day 1 | Day 2 | Day 3 | Day 4 | Day 5
58 | 49 | 46 | 45 | 45