## Sprint 2 Backlog
|  |  | Points Remaining |  | Points Completed
Story | Tasks | Points |  | Assignees | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Complete
As a user I can select the number of questions in the quiz | Link host settings with backend | 3 | 0 | Rauf, Robert |  | 2 | 1 |  |  | Yes
| Finish host settings page | 4 | 0 | Mikhail |  |  |  | 2 | 2 | Yes
As a user I can set the time limit to each question in the quiz | Link host settings with backend | 4 | 0 | Rauf,Robert |  |  |  | 3 | 1 | Yes
As a user I would like to see the current state of the quiz | Create working lobby for host with start game functionality | 4 | 0 | Rauf,Robert |  |  |  | 2 | 2 | Yes
| Render questions from API in frontend | 2 | 0 | Rauf, Robert | 2 |  |  |  |  | Yes
| create end screen | 4 | 0 | Alek |  |  |  | 2 | 2 | Yes
As a user I would like to be able to host a multiplayer quiz | Integrate into frontend multiplayer functions backend | 3 | 0 | Rauf, Robert |  |  | 2 | 1 |  | Yes
| Add the calls to the backend into the frontend for multiplayer integration | 3 | 0 | Rauf, Robert |  |  |  | 1 | 2 | Yes
As a user I can select the category of the questions in the quiz | Investigate model for organisation in the database | 2 | 0 | Jason |  | 2 |  |  |  | Yes
| Integrate with frontend | 2 | 0 | Jason |  |  |  | 2 |  | Yes
As a user I would like to be able to join a quiz | Integrate with the frontend, create API call for joining | 2 | 0 |  |  |  | 1 | 1 |  | Yes
| Create join page | 4 | 0 | Lachlan |  |  | 4 |  |  | Yes
As a user I would like to see my own score of the quiz against the other players | Send scores to frontend | 2 | 0 | Rauf, Robert |  | 2 |  |  |  | Yes
| Send scores to backend | 2 | 0 | Rauf , Robert |  | 2 |  |  |  | Yes
As a user I would like a quiz that I can access on my laptop, phone or tablet | Scaling for different screensizes: Host settings | 5 | 0 | Matt, mikhail | 2 |  |  | 2 | 1 | Yes
| Scaling for different screensizes: Settings page | 2 | 0 | Matt |  | 2 |  |  |  | Yes
| Scaling for different screensizes: Leaderboard | 2 | 0 | Matt |  |  | 2 |  |  | Yes
| Scaling for different screensizes: Instructions | 2 | 0 | Matt |  |  |  | 2 |  | Yes
| Scaling for different screensizes: End Screen | 2 | 0 | Matt |  |  |  |  | 2 | Yes
As a user I can set my own name/nickname for the game | Send nickname to backend |  | 0 | [6 empty] | Yes
As a user I can see the instructions to the game | Set finalised instructions | 1 | 1 | [6 empty] | No
As a user I can reconnect to the same game if I disconnect | Research into cookie | 2 | 0 | Jason | 1 | 1 |  |  |  | Yes
| Develop Backend Functionality | 2 | 2 | [6 empty] | No
As a user I can use powerups to aid me in the quiz | Decide what they should be | 3 | 0 | Matthew | 1 | 2 |  |  |  | Yes
| Design UI for the app |  | 0 | Matthew | [5 empty] | Yes
As a user I can see my score between Questions | Research the possibility of a bufferscreen | 2 | 0 | Lachlan |  |  |  | 2 |  | Yes
Teams integration | Research | 4 | 0 | Lachlan | 1 | 3 |  |  |  | Yes
As a user I can view a leaderboard of scores for the current game |  |  | 0 | [6 empty] | Yes
Testing | Unit Testing | 5 | 5 | [6 empty] | No
| User testing | 5 | 5 | [6 empty] | No
AS A user I would like to have a buffer page between each question so I can check what is happening with the quiz | Implement Design of page | 3 | 0 | Lachlan |  |  |  | 1 | 2 | Yes
Update Documentation | Daily Notes | 5 | 0 | Lachlan | 1 | 1 | 1 | 1 | 1 | Yes
| Report | 10 | 0 | Lachlan | 2 | 1 | 2 | 2 | 3 | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes
|  |  | 0 | [6 empty] | Yes

## Team Roster
Name | Matriculation Number | Email Address

## Analytics
Total Points for Sprint
96 |  |  |  | 0
Points Remaining
Day 1 | Day 2 | Day 3 | Day 4 | Day 5
86 | 68 | 55 | 31 | 13